## Project Planner
WD in PHP Project
| ICBT Aslam Anver 68/24 | [7 empty] | Period Highlight: | 2017-05-28 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY | START DATE | FINISH DATE | DURATION PERIOD | DAYS REMAIN | ACTUAL START | ACTUAL FINISH | ACTUAL DAYS | PERCENT COMPLETE | 9-M | 9-T | 9-W | 9-T | 9-F | 9-S | 10-S | 10-M | 10-T | 10-W | 10-T | 10-F | 10-S | 11-S | 11-M | 11-T | 11-W | 11-T | 11-F | 11-S | 12-S | 12-M | 12-T | 12-W | 12-T | 12-F | 12-S | 13-S | 13-M | 13-T | 13-W | 13-T | 13-F | 13-S | 14-S | 14-M | 14-T | 14-W | 14-T | 14-F | 14-S | 15-S | 15-M | 15-T | 15-W | 15-T | 15-F | 15-S | 16-S | 16-M | 16-T | 16-W | 16-T | 16-F | 16-S | 17-S | 17-M | 17-T | 17-W | 17-T | 17-F | 17-S | 18-S | 18-M | 18-T | 18-W | 18-T | 18-F | 18-S | 19-S | 19-M | 19-T | 19-W | 19-T | 19-F | 19-S | 20-S | 20-M | 20-T | 20-W | 20-T | 20-F | 20-S | 21-S | 21-M | 21-T | 21-W | 21-T | 21-F | 21-S | 22-S | 22-M | 22-T | 22-W | 22-T | 22-F | 22-S | 23-S | 23-M | 23-T | 23-W | 23-T | 23-F | 23-S | 24-S | 24-M | 24-T
 | time axis 2017-02-27 to 2017-06-13
1 | Introduction and executive summary. | 2017-05-15 | 2017-05-16 | 2 | 0 | 2017-05-15 | 2017-05-16 | 2 | 100%
2 | Requirements gathering and prepare software requirement specification | 2017-05-16 | 2017-05-18 | 3 | 0 | 2017-05-16 | 2017-05-18 | 3 | 100%
3 | Develop the website | 2017-05-18 | 2017-05-25 | 8 | 0 | 2017-05-18 | 2017-05-25 | 8 | 100%
4 | Demonstrate the system | 2017-05-25 | 2017-05-27 | 3 | 0 | 2017-05-25 | 2017-05-27 | 3 | 100%
5 | Testing the system | 2017-05-27 | 2017-05-28 | 2 | 0 | 2017-05-27 | 2017-05-28 | 2 | 100%

## Project Planner Expend
ICBT - CMS Project Planning
ICBT Batch 68, Team,Project Lead - Aslam & Pavithran | [11 empty] | Period Highlight: | 2017-05-28 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan) | [8 empty] | Finished |  |  | Not started |  |  |  | Deadline is near
| SDLC | ACTIVITY | RESPONSIBLE | START DATE | FINISH DATE | DURATION PERIOD | DAYS REMAIN | ACTUAL START | ACTUAL FINISH | ACTUAL DAYS | ANY NOTES | PERCENT COMPLETE | 9-M | 9-T | 9-W | 9-T | 9-F | 9-S | 10-S | 10-M | 10-T | 10-W | 10-T | 10-F | 10-S | 11-S | 11-M | 11-T | 11-W | 11-T | 11-F | 11-S | 12-S | 12-M | 12-T | 12-W | 12-T | 12-F | 12-S | 13-S | 13-M | 13-T | 13-W | 13-T | 13-F | 13-S | 14-S | 14-M | 14-T | 14-W | 14-T | 14-F | 14-S | 15-S | 15-M | 15-T | 15-W | 15-T | 15-F | 15-S | 16-S | 16-M | 16-T | 16-W | 16-T | 16-F | 16-S | 17-S | 17-M | 17-T | 17-W | 17-T | 17-F | 17-S | 18-S | 18-M | 18-T | 18-W | 18-T | 18-F | 18-S | 19-S | 19-M
 | time axis 2017-02-27 to 2017-05-08
1 | RG | Proposal preparation for the entire project which are going to be implemented by our team | Team | 2017-02-27 | 2017-03-05 | 7 | 0 | 2017-02-27 | 2017-03-05 | 7 |  | 100%
2 | SD | Find a better template design for website and backend | Team | 2017-03-07 | 2017-03-11 | 5 | 0 | 2017-03-07 | 2017-03-11 | 5 |  | 100%
3 | RG | Onsite Observation with IT director & IT Team to requirements gathering | Aslam, Harish | 2017-02-27 | 2017-02-27 | 1 | 0 | 2017-02-27 | 2017-02-27 | 1 |  | 100%
4 | RG | Operational Feasibility - Preliminary Investigation | Who ? | 2017-03-13 | 2017-03-14 | 2 | 0 | 2017-03-13 | 2017-03-14 | 2 |  | 25%
5 | RG | Legal Feasibility - Preliminary Investigation | Who ? | 2017-03-14 | 2017-03-14 | 1 | 0 | 2017-03-14 | 2017-03-14 | 1 |  | 0%
6 | RG | Economic Feasibility - Preliminary Investigation | Who ? | 2017-03-15 | 2017-03-15 | 1 | 0 | 2017-03-15 | 2017-03-15 | 1 |  | 0%
7 | RG | Decision Table for students and courses | Who ? | 2017-03-15 | 2017-03-15 | 1 | 0 | 2017-03-15 | 2017-03-15 | 1 |  | 0%
8 | RG | Technical Feasibility - Preliminary Investigation | Who ? | 2017-03-16 | 2017-03-17 | 2 | 0 | 2017-03-16 | 2017-03-17 | 2 |  | 0%
9 | SD | Context Level Diagram (Data Flow Diagram) | Who ? | 2017-03-18 | 2017-03-18 | 1 | 0 | 2017-03-18 | 2017-03-18 | 1 |  | 0%
10 | SD | 0th Level Diagram (Data Flow Diagram) | Who ? | 2017-03-18 | 2017-03-18 | 1 | 0 | 2017-03-18 | 2017-03-18 | 1 |  | 0%
11 | SD | 1st Level Diagram (Data Flow Diagram) | Who ? | 2017-03-19 | 2017-03-19 | 1 | 0 | 2017-03-19 | 2017-03-19 | 1 |  | 0%
12 | SD | Structure Diagram (Data Flow Diagram) | Who ? | 2017-03-19 | 2017-03-19 | 1 | 0 | 2017-03-19 | 2017-03-19 | 1 |  | 0%
13 | SD | Use Case Diagram (UML) | Who ? | 2017-03-20 | 2017-03-20 | 1 | 0 | 2017-03-20 | 2017-03-20 | 1 |  | 0%
14 | SD | Psudo Code | Who ? | 2017-03-20 | 2017-03-20 | 1 | 0 | 2017-03-20 | 2017-03-20 | 1 |  | 0%
15 | SD | Class Diagram (UML) | Who ? | 2017-03-21 | 2017-03-22 | 2 | 0 | 2017-03-21 | 2017-03-22 | 2 |  | 0%
16 | SD | Entity Relationship Diagram | Who ? | 2017-03-23 | 2017-03-23 | 1 | 0 | 2017-03-23 | 2017-03-23 | 1 |  | 0%
17 | SD | Relational Schema | Who ? | 2017-03-24 | 2017-03-24 | 1 | 0 | 2017-03-24 | 2017-03-24 | 1 |  | 0%
18 | SD | Database Normalization | Who ? | 2017-03-25 | 2017-03-25 | 1 | 0 | 2017-03-25 | 2017-03-25 | 1 |  | 0%
19 | RG | 360 Degree photo capture session | Murali | 2017-03-25 | 2017-03-28 | 4 | 0 | 2017-03-25 | 2017-03-28 | 4 |  | 0%
20 | DEV | Website designing of ICBT domain | Aslam, Pavi | 2017-03-13 | 2017-03-23 | 11 | 0 | 2017-03-13 | 2017-03-23 | 11 |  | 0%
21 | DEV | Content Management System Designing | Aslam, Pavi | 2017-03-24 | 2017-04-01 | 9 | 0 | 2017-03-24 | 2017-04-01 | 9 |  | 0%
22 | DEV | Database Development | Aslam, Pavi | 2017-04-02 | 2017-04-06 | 5 | 0 | 2017-04-02 | 2017-04-06 | 5 |  | 0%
23 | TEST | Database Testing (QAE should put dummy data) | Murali, Amalan | 2017-04-07 | 2017-04-08 | 2 | 0 | 2017-04-07 | 2017-04-08 | 2 |  | 0%
24 | DEV | Web development of ICBT domain in server side | Aslam, Pavi | 2017-04-09 | 2017-04-17 | 9 | 0 | 2017-04-09 | 2017-04-17 | 9 |  | 0%
25 | DEV | Build web content management system through chosen programming languages such of PHP server side and Javascript client side | Aslam, Pavi | 2017-04-18 | 2017-04-26 | 9 | 0 | 2017-04-18 | 2017-04-26 | 9 |  | 0%
26 | TEST | ICBT Website testing and Quality assurance | Murali, Amalan | 2017-04-27 | 2017-04-29 | 3 | 0 | 2017-04-27 | 2017-04-29 | 3 |  | 0%
26 | TEST | ICBT CMS & System testing and Quality assurance | Murali, Amalan | 2017-04-30 | 2017-05-03 | 4 | 0 | 2017-04-30 | 2017-05-03 | 4 |  | 0%
27 | IM | System demonstration, implementation and training for the staff | Team | 2017-05-04 | 2017-05-07 | 4 | 0 | 2017-05-04 | 2017-05-07 | 4 |  | 0%

## Meetings
Meetings
ICBT CMS Development project
No | Name | DATE | START | FINISH | DURATION |  | MEMBERS | CONCLUSION
MEDIUM
1 | Proposal Planning | 2017-03-04 | 9:00 | 12:00 | 3:00 | Direct | Team | Got ideas about proposal preparation.
2 | Project Planing | 2017-03-11 | 11:00 | 13:00 | 2:00 | Direct | Aslam, Pavithran | Preparation for project planning and assign roles.
3 | ICBT Project Beginning | 2017-03-13 | 22:05 | 23:40 | 1:35 | Zoom | Team | Preparing for the presentation of proposal and start the project with taken instructions
4

## Sheet2
Website security information
ICBT CMS Development project
1 | Website Domain | http://icbt.nflogistic.com
2 | Databse Name | icbtcms
3 | Databse Super User | icbt | Assigned all privileges
4 | Databse Password | ***
5 | FTP Host / Server | ftp.nflogistic.com
6 | FTP Port | 21
7 | FTP Username | icbt
8 | FTP Password | ***
9 | phpMyAdmin | http://sys.nflogistic.com/phpmyadmin | Database Login Required
10 | File Manager Simple | http://sys.nflogistic.com/mftp/ | FTP Login Required
11 | File Manager Advanced | http://sys.nflogistic.com/filemgr/ | Username : icbt / Password : ***